## Sheet4
How to use the BPI Road Map: This document is intended as a guide for BPI team leads and facilitators as they navigate Business Process Improvement tools and templates. It is illustrative of one project implementation plan. Time allocated to each step is dependent upon many factors including: experience of the team lead; process scope and complexity; number of participants; duration of project. Using this outline, a team lead or facilitator should make adjustments to accommodate his/her unique project.
Step | Goals | Schedule | Team Lead Preparation | Meeting Activities and Deliverables | Team Lead | Participant | SME | Work
Initiate |  | Week 1 Pre-work | Review all BPI material at improve.ucsf.edu |  | 0 |  |  | In mtg
|  |  | Decide if you want to contract for PMO help |  | 16 |  |  | Out mtg
| Draft charter |  | Preliminary process selection, charter, schedule
| Draft schedule |  | Select & notify team
| Team set-up |  | Schedule team meetings
| Logistics |  | Design first meeting outcomes, agenda, materials
| Communication |  | Email to team with invitation and assignment
Determine tools to support work (file sharing, conf call, email protocols, etc.)
Communicate with unit & articulate mgmt support
Register project by posting in Box
|  | Week 2 2 hr Mtg | Preview materials and plan team instructions | In Meeting: | 2 | 2 |  | In mtg
|  |  | Send agenda | Go through “Initiate” slides | 8 | 2 |  | Out mtg
| Get buy-in |  |  | Agree on roles, time commitment, and schedule
| Clarify roles |  |  | Preview tools that support the team’s work
| Finalize charter |  |  | Evaluate goal statement; is it SMART?
Homework after:
Write final project schedule and charter
Post charter on-line
Explore |  | Week 3 2 hr Mtg | Preview materials and plan team instructions | In Meeting: | 2 | 2 |  | In mtg
|  |  | Send agenda | Go through “Explore” slides | 8 | 4 |  | Out mtg
| Learn mapping |  | Bring flip chart/markers/ post-its | Discuss customers, process
| ID customers |  |  | Begin high level process maps (current state)
| Scope process |  |  | Discuss info needed to continue mapping (and from whom)
Homework after:
Interview Customers and SMEs; invite to next mtg if needed
Compile results of discussion (and map)
|  | Week 4 4 hr Mtg | Preview materials and plan team instructions | In Meeting: | 4 | 4 | 4 | In mtg
|  |  | Send agenda | Complete mapping | 6 | 4 | 4 | Out mtg
| Map current state |  | Review notes from previous meeting | ID metrics needed: e.g. customers, time, error, etc
| ID metrics |  | Bring flip chart/markers/ post-its
|  |  | Ensure SME/Customer guests have mtg info | Homework after:
Create data gathering tools
Gather data
Transcribe map
|  | Week 5 No Mtg | Support participants in task | In Meeting: | 0 | 0 |  | In mtg
[5 empty] | 8 | 6 | 4 | Out mtg
Collect map info
| Collect metric info |  |  | Homework after:
| Collect other data |  |  | Continue gathering and compiling data
|  | Week 6 4 hr Mtg | Preview materials and plan team instructions | In Meeting: | 4 | 4 | 4 | In mtg
|  |  | Send agenda | Go through "Improve" slides | 10 | 4 | 4 | Out mtg
| Finalize map(s) |  | Review notes from previous meeting | Review and finalize map - assign times
| Begin analysis |  | Bring flip chart/markers/post-its | Add other metrics; consider waste, NVA, bottleneck
| Apply metrics |  |  | Conduct root cause analysis
Improve |  |  |  | Capture improvements in "parking lot" but don’t focus there
Homework after:
Think about map problems
Document outcomes
Ask more questions & get more data on key areas
|  | Week 7 4 hr Mtg | Who sets criteria for priority; if outsider get criteria | In Meeting: | 4 | 4 | 4 | In mtg
|  |  | Confirm who will "decide" which improvements | Review root cause list | 10 | 6 | 4 | Out mtg
| ID improvements |  | Preview materials and plan team instructions | Brainstorm improvements and then add detail to top ideas
| Prioritize |  | Send agenda | Set criteria for prioritizing improvements
| Map "to be" |  | Review notes from previous meeting | Prioritize improvements against criteria
Homework after:
Think about results; get more info if needed
Document outcomes
If outsider must decide or endorse improvements, set mtg
|  | Week 8 2 hr Mtg | Preview materials and plan team instructions | In Meeting: | 2 | 2 |  | In mtg
|  |  | Send agenda | Discuss priority work from last meeting | 10 | 6 | 4 | Out mtg
| Recommend |  | Review notes from previous meeting | Discuss obvious improvements; discuss outliers
| Refine improv'ts |  |  | Agree on recommendations to Decision maker(s)
Begin to refine and add more detail on selected improvements
Homework after:
Document outcomes
Assign work to add detail to recommended improvements
Create presentation document for decision maker
|  | Week 9 1 hr Mtg | Preview materials and plan team instructions | In Meeting: | 1 | 1 |  | In mtg
| Recap work |  | Send agenda | Present work and recommendations | 8 | 4 |  | Out mtg
| Decide next steps |  |  | Decide scope of implementation
Get buy-in
Homework after:
Document Decision
Continue work on detail of all recommended improvements
|  | Week 10 4 hr Mtg | Review & QA homework – draft detail improvements | In Meeting: | 4 | 4 |  | In mtg
|  |  | Preview materials and plan team instructions | Review draft detail of recommended improvements | 10 | 6 |  | Out mtg
| Future state map |  | Send agenda | Map future state process; add design detail and other info
| Draft schedule |  |  | Go through "Implement" slides
| Target measures |  |  | Draft implementation schedule
Create target measures
Implement |  |  |  | Assign Action Plan and design detail
Homework after:
Document maps, action plans, target metrics, schedule
Continue work on design detail and action plans
|  | Week 11 No Mtg | Support participants in task | In Meeting: |  |  |  | In mtg
| Draft action plans |  |  |  | 8 | 6 | 4 | Out mtg
Homework after:
Continue work on design detail and action plans
|  | Week 12 2 hr Mtg | Preview materials and plan team instructions | In Meeting: | 3 | 3 |  | In mtg
|  |  | Send agenda | Review and confirm action plans, schedule, metrics, etc. | 12 | 6 |  | Out mtg
| Final implementation |  |  | Discuss & create change management & training plan
| plans |  |  | Agree on status reporting method and timing
| Communication plan |  |  | Discuss lessons learned
Training plan
| Lessons learned |  |  | Homework after:
Document outcomes
Begin implementation tasks per schedule
| Completed | Week 13 2 hr Mtg | Draft and send communications per plan | In Meeting: | 2 | 2 | 2 | In mtg
| implementation |  | Draft and begin training | Status on tasks accomplished | 12 | 6 |  | Out mtg
| tasks |  | Preview materials and plan team instructions | Go through “Celebrate” slides
Complete Implementation tasks per plan
Homework after:
Continue implementation tasks
Track progress via status
| Completed | Weeks 15-18 | Plan Celebration / Recognition | In Meeting |  |  |  | In mtg
| implementaiton |  | Check in with implementers per project schedule | Homework after: | 48 | 32 | 16 | Out mtg
| tasks |  | Complete Implementation tasks per plan | Report status on implementations
Celebrate |  |  |  | Continue implementation tasks and change management
Check progress against future state metrics
|  | Week 19 2 hr Mtg & event to celebrate | Send invite/agenda | In Meeting: | 2 | 2 |  | In mtg
| Recognize |  | Check in with implementers per project schedule | Final Status report on implementation steps | 8 | 2 |  | Out mtg
| Publicize |  | Document measures against target metrics | Recognize accomplishments
Final documentation of accomplishments
Communicate / publicize accomplishments
Post results in Box on Improve.ucsf.edu